## Feature Toggle Dashboard
Feature Toggle Dashboard
S.No. | Feature Name | Impact | Release | Target | Date Created | Team | QA Owner | Team Server | DEVINT | QA3 | UAT1 | UAT2 | PA | PROD | PROD On Date | Expected PROD ML STATUS | Expected HONDA PROD STATUS | Feature/User Story/Defect PR | Feature/User Story/Defect Remove PR | Feature Removal Version | Date Removed
1 | contract_nutsandbolts_2019_q2_s2 | DMS Import edit contract | 2.6 |  | 2019-05-20 | Nuts and Bolts | Shawket | ON | OFF | ISSUE | ISSUE | OFF | ISSUE | OFF |  | ON |  | nutsandbolts_q2_s2 | nutsandbolts_remove_pr_q2_s2
2 | contract_nightswatch_2019_q2_s3 Note: When turned on it impact technocrats change for DE67977 so this is turned off until technocrats comes in with a fix | Contract Verification Expire | 2.61 |  | 2019-05-29 | Nights Watch | Pavani | ON | ON | ON | OFF | OFF | OFF | OFF |  |  |  | https://ghe.coxautoinc.com/DT-SFI/dt/pull/41
3 | contract_falcons_q2_s2_de60013 | Lease Fee Model | 2.60.5 |  | 2019-05-28 | Falcons | Shobhit Bajaj | ON | ON | ON | ON | OFF | ON | OFF |  | OFF |  | falcon_q2_s2_de60013
4 | contract_enciphers_2019_q2_s1__de52636 | Trailing docs flow in 'Docs Received' status | 2.59.5 |  | 2019-05-16 | Enciphers | Shradha More | OFF | OFF | OFF | ON | OFF | OFF | OFF |  |  |  | DE52636
5 | contract_enciphers_2019_q2_s3 | Capitalized hard adds model window | 2.60.2 |  | 2019-06-04 | Enciphers | Shradha More | OFF | OFF | OFF | ON | OFF | OFF | OFF |  | OFF |  | DE60692
6 | contract_enciphers_2019_q2_s3 | Additional docs added via i-Pad using plus sign and contract is expired | 2.61.0 |  | 2019-06-11 | Enciphers | Shradha More | ON | ON | ON | ON | OFF | ON | OFF |  |  |  | DE55945
7 | fugu_async | Verification Response | 2.61 |  | 2019-04-09 | Pink Team | Najeeb Faridi | OFF | ON | ON | ON | ON | ON | ON |  | ON |  | fugu_async
8 | Contract_PinkTeam_sbmv_performance | Route based validation, save on continue, Submit for verification | 2.61 |  | 2019-05-20 | Pink Team | Najeeb Faridi | OFF | ON | OFF | OFF | OFF | OFF | OFF |  | OFF |  | Contract_PinkTeam_sbmv_performance
9 | Contract_PinkTeam_remove_cache | Removing caching for long sized objects | 2.61 |  | 2019-05-29 | Pink Team | Najeeb Faridi | OFF | ON | OFF | OFF | OFF | OFF | OFF |  | OFF |  | Contract_PinkTeam_remove_cache
10 | Contract_nightswatch_DE57199_2019_Q2_S1 | DMS imports to AHFC - Rate Modifiers | 2.59.4 |  | 2019-05-14 | Nights Watch | Pavani | ON | ON | ON | ON | ON | ON | ON |  |  |  | DE57199 | https://ghe.coxautoinc.com/DT-SFI/dt/pull/363 |  | 6/25/2019(2.62)
11 | contract_avengers_2019_Q2_S3_US220764 | Print Billing Address on Credit App PDF | 2.60.1 |  | 2019-05-29 | Avengers | Maruthi Mettela | ON | ON | ON | ON |  | ON |  |  | ON |  | US220764
12 | contract_avengers_US212425_2019_Q2_S2 | Stipulations are not displayed on Funding Package screen just after decisioning | 2.60.1 |  | 2019-05-29 | Avengers | Anushree Roy | ON | ON | ON | ON |  | ON |  |  | ON |  | US212425
13 | contract_avengers_2019_q2_s3 modifiers_page_spot_flow | CR 46700 Modifier Page for Spot Lease Acquisition Fee | 2.60.3 |  | 2019-06-10 | Avengers | Prasad Kirpekar | ON |  | ON | ON |  | ON |  |  | ON |  | US212496
14 | contract_avengers_2019_Q2_S3 | Able to see corporate resolution documents twice in FPP for a Spot flow | 2.60.1 |  | 2019-05-29 | Avengers | Anushree Roy | ON | ON | ON | ON |  | ON |  |  | ON |  | DE58425
15 | Contract_Technocrats_US247941_2019_Q2 | Category changes for cash price other fees, Fee Category | 2.60.5 |  | 2019-06-12 | Technocrats | Naveed Khan | OFF | ON | OFF | ON | OFF | ON | OFF |  |  |  | US247941 | US272782 |  | 31/07/2019
16 | contract_technocrats_2019_q2_s4_de60302 | cap_cost_reduction_cost tax without payment method for DMS import | 2.60.6 |  | 2019-06-15 | Technocrats | Amit Pandey | OFF | ON | OFF | ON | OFF | OFF | OFF |  |  |  | DE60302 | US272782 |  | 31/07/2019
17 | contract_param_2019_q2_s4 | One pay lease | 2.60.4 |  | 2019-06-12 | Param | Kiran Borwake | ON | ON | OFF | ON | OFF | ON | OFF |  | ON |  | DE61819, US243590
18 | contract_param_2019_q2_s4 | Continue button / Submit for verification on Finance page, Additional information page. | 2.60.5 |  | 2019-06-18 | Param | Sinkita Jain | ON | ON | OFF | ON | OFF | ON | OFF |  |  |  | DE61623, DE62485, DE63425
19 | contract_param_2019_q2_s4_DE60013 | UAT1 - Porsche/NMAC- Lease Fee Module is displaying fees as required intermittently when they are not required for certain lenders- (NMAC034) | 2.60.5 |  | 2019-06-17 | Param | Sinkita Jain | ON | ON | OFF | ON | OFF | ON | OFF |  |  |  | DE60013
20 | Contract_Technocrats_US247941_2019_Q2 DUPLICATE OF LINE #15 |  |  |  |  | Technocrats |  |  |  |  | ON
21 | dms_ins_filter | FIlter insurance data for DMS import json | 2.60.6 |  | 30th May 2019 | Falcons | Shhobhit Bajaj | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE58283
22 | Contract_PARAM_2019_Q2_2 | Fixes for NMac Retail | 2.60.0 |  | 2019-05-21 | Param |  | ON | ON | OFF | ON | OFF | OFF | OFF |  | OFF |  | US238897
23 | contract_falcons_2019_q2_s4__de60735 | Extra miles for NMAC | 2.60.5 |  | 2019-06-14 | Falcons | Shobhit Bajaj | ON | ON | ON | ON | OFF | ON | OFF |  |  |  | DE60735
24 | contract_param_2019_q2_s3 | image tag for COF | 2.60.2 |  | 2019-06-10 | Param | Kiran Borwake | ON | OFF |  | ON |  | ON |  |  | ON |  | DE61188
25 | contract_param_2019_q2_s3 | Property tax field in finance section | 2.60.2 |  | 2019-06-06 | Param | Kiran Borwake | ON | ON |  | ON |  |  |  |  | ON |  | DE60566
26 | contract_falcons_2019_q2_s3__de54719 | Contract SubmittedDeal Feature Status is 'Contract Submitted' even when Submit for Funding Transaction Fails | 2.60.4 |  |  | Falcons | Shobhit Bajaj | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE54719
27 | dcon_lease_modal | Taxes and Fees Lease modal window | 2.6 |  | 2019-05-21 | Falcons | Shobhit Bajaj | ON | ON | ON | ON | OFF | ON | OFF |  | OFF |  | DE57277
28 | enable_browser_signing | Enable sign button on uniFI(default disable) | 2.6 |  |  | Formidables | Danish |  |  |  | ON | [6 empty] | US224848
29 | nmac_pilot_atomic_xml | Enable atomic xml for NIS for specific states | 2.60.2 |  | 2019-05-21 | Param | Kiran Borwake | ON | ON | ON | ON |  | ON |  |  |  |  | US229666
30 | chase_feature_toggle | Allow Ancillary and POS documents to be submitted | 2.60.0 |  | 2019-05-21 | Param | Shradha More | OFF | ON |  | ON | [6 empty] | US239521
31 | contract_avengers_2019_q2_s3_DE62851 | On re-submission of Credit app with Stipulations, Decision tab remains in 'Pending' status. | 2.6 |  |  | Avengers | Anushree Roy |  |  |  | ON |  | ON |  |  | ON |  | DE62851
32 | coapp_ssn_validation | User is able to proceed without entering SSN for the co-applicant. | 2.6 |  |  | Avengers | Anushree Roy |  |  |  | ON |  | ON |  |  | ON |  | DE61312
33 | dob_under_eighteen | Speed zone Motorsports Applicant DOB <18 not blocked | 2.6 |  |  | Avengers | Maruthi Mettela |  |  |  | ON |  | ON |  |  | ON
34 | ContractAvengers_2019_Q2_S3 | User is allowed to continue for older models when changed from used to new | 2.6 |  |  | Avengers | Anushree Roy |  |  |  | ON |  | ON |  |  | ON
35 | contract_avengers_2019_Q2_S2_DE59481 | MC_Trade-in details in Contract Vehicle page is getting wiped out on resubmission of Credit app. | 2.60,2.61.6 |  |  | Avengers | Anushree Roy | ON |  |  | ON |  | OFF |  |  | OFF |  | DE59481
36 | contract_avengers_2019_Q2_S3_DE63568 | UAT1 AHFC Non-auto Estimated amount financed is not correct for MC credit application when trade in is entered | 2.60.7 |  |  | Avengers | Maruthi Mettela | ON | OFF | ON | ON | OFF | ON | OFF |  |  |  | DE63568
37 | contract_falcons_2019_q2_s5__de63529 | Credit application and other ancillary documents are not displayed in funding | 2.60.7 |  |  | Falcons | Shobhit Bajaj | ON | ON | ON | ON |  | ON |  |  | ON
38 | contract_param_2019_q2_s5_DE63340 | Honda maintanance provider | 2.60.7 |  | June 19,2019 | Param | Kiran Borwake | ON | ON | ON | ON |  | ON
40 | contract_pinkteam_2019_q2_s5 |  | 2.62.0 |  |  | Pink Team | Najeeb | ON | ON | ON | ON | ON | ON | ON |  | ON
41 | contract_resubmit | Submit for funding is allowed any number of times after contract Return | 2.61.0 |  | 2019-06-14 | Enciphers | Shradha More | ON | ON | ON | ON | [6 empty] | US234959 , US231365 , DE63394
42 | contract_technocrats_2019_q2_s4_us252913 | Verification expiration logic | 2.61.3 |  | June 25,2019 | Technocrats | Amit Pandey | ON | ON | ON | ON | [6 empty] | US252913
43 | contract_falcons_2019_q2_s5__de62571 | DigCon-UniFi-DMS Import - On Capitalized Hard adds DMS Import pre-populated data can not be overwrite with different value. | 2.61.3 |  | June 25,2019 | Falcons | Shobhit Bajaj | ON | ON | ON | ON |  | ON |  |  |  |  | DE62571
44 | contract_param_2019_q2_s5 | Property tax value on UI gets wiped out on change event of any field on Additonal Info page. | 2.61.3 |  | June 26,2019 | Param | Sinkita | ON | ON | ON | ON | [6 empty] | DE63759
45 | contract_param_2019_q2_s5__de59087 dcon_lease_modal contract_falcons_q2_s2_de60013 contract_param_2019_q2_s4_DE60013 | Modal window clean up issue - TEAM REVIEWING | 2.61.3 |  | June 27,2019 | Param | Kiran Borawake | ON | ON | ON | ON |  | ON |  |  |  |  | DE59087
46 | contract_param_2019_q2_s5__de32019 | ML Lease - Expression Validation of Security Deposit | 2.61.3 |  | June 27,2019 | Param | Kiran Borawake | ON | OFF | ON | ON | [6 empty] | DE32019
47 | contract_falcons_2019_q2_s5__de63197 | NMAC/IFS-LEASE-FL-Invoice _amt tag is missing in xml for FL State | 2.61.3 |  | June 27,2019 | Falcons | Shobhit Bajaj | ON | ON | ON | ON |  | ON |  |  |  |  | DE59087
48 | contract_param_2019_q2_s5__de64481 contract_param_2019_q2_s4 | LEASE-NMAC/IFS-FL-On editing contract ,Continue button is appearing on contract finance page expected Submit button (for garaging state NY) | 2.61.3 |  | June 27,2019 | Param | Kiran Borawake | ON | OFF | ON | ON | [6 empty] | DE64481
49 | contract_avengers_2019_q2_s5_de31710 | Dealer unable to see Turndown due to Unicode Character in Comment - SUPP-1051308 - REVIEWED | 2.61.2 |  | June 21,2019 | Avengers | Prasad Kirpekar | ON | OFF | ON | ON | OFF | ON | OFF |  |  |  | DE31710
50 | contract_avengers_2019_q2_s5_de57739 | AHFC - P3 - All Stipulations with or without docs disappear from details page when trailing docs are resubmitted after Contract is suspended | 2.61.2 |  | June 21,2019 | Avengers | Anushree Roy | ON | OFF | ON | ON | OFF | ON | OFF |  |  |  | DE57739
51 | contract_avengers_2019_q2_s5_de61779 | AHFC-QAT3(2.60.1) Honda Spot flow: On entering proper Vin and other details, on click of Save, the validation messsage remains for ‘Invoice’ field. Even though the data has been populated | 2.61.2 |  | June 24,2019 | Avengers | Anushree Roy | ON | OFF | ON | ON | OFF | ON | OFF |  |  |  | DE61779
52 | contract_pinkteam_2019_q2_s5_de54058 Note: when this was turned on it impacted we were losing the tax on cap cost reduction. | lender presets on applicant, coapplicant, vehicle, finance forms | 2.62.0 |  | 2019-06-28 | Pink Team | Najeeb Faridi | OFF | ON | OFF | OFF | OFF | OFF | OFF |  | OFF |  | DE54058
53 | contract_technocrats_2019_q2_s5__de64948 | County not visible for AFC and GFR lenders | 2.60,2.61 |  | 2019-07-01 | Technocrats | Naveed Khan | OFF | ON | ON | ON |  | OFF |  |  |  |  | DE64948 | US272782 |  | 31/07/2019
54 | contract_enciphers_2019_q2_s5 | Hiding 'Other' option for Billing Address field, for lease product type for GFR lender | 2.62.0 |  | 2019-07-03 | Enciphers | Shradha More | ON | ON | ON | ON | OFF | OFF | OFF |  | ON |  | US215827
55 | contract_technocrats_2019_q2_s5__de65507 | Pilot Atomic XML Generation | 2.61.5 |  | 2019-07-03 | Technocrats | Amit Pandey | ON | ON | ON | ON |  | ON |  |  |  |  | DE65507
56 | time_it | Log time taken by individual method with @timeit() | 2.61 |  | 2019-07-01 | Pink Team | Najeeb Faridi | OFF | ON | OFF | OFF | OFF | OFF | OFF |  | OFF |  | US234477
57 | contract_falcons_2019_q2_s5__de63410 | Verification Request give 500 Error on UAT1 | 2.61.4 |  |  | Falcons | Shobhit Bajaj | ON | ON | ON | ON |  | ON
58 | contract_falcons_2019_q2_s5__de59250 | Issues observed in guarantor functionality for business with co-application deal type | 2.62.0 |  | 2019-07-09 | Falcons | Shobhit Bajaj | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE59250
59 | contract_avengers_2019_q2_s5__de57737 | AHFC - P3_DT_2.57- Regression - iContracting - All comments given for the checklist item are displayed in ideal when it is suspended multiple times instead of latest comments | 2.61.5 |  | July 8,2019 | Avengers | Anushree Roy | ON | OFF | ON | ON | OFF | ON | OFF |  |  |  | DE57737
60 | contract_avengers_2019_q2_s5_us234804 | CR 46776 Address Validation Zip plus 4 | 2.61.5 | "targets": [ { "excludes": [], "includes": [ 1087927 ], "name": "dealer_code", "arg": "dealer_code" } ] | July 8,2019 | Avengers | Prasad Kirpekar | ON | OFF | ON | ON | ON | OFF | OFF |  |  |  | US234804
61 | contract_avengers_2019_q2_s5_DE47914 | QC7905/Mobile/Cell number once entered persist on UI & PDF even after edited or removed | 2.61.5 |  | July 5,2019 | Avengers | Anushree Roy | ON | OFF | ON | ON | OFF | ON | OFF |  |  |  | DE47914
62 | contract_falcons_2019_q2_s5__de61143 | Texas Personal Property Tax Guide is signing no responsibility regardless of selections (More or less than 50%) for Nissan | 2.61.6 |  | July 8.2019 | Falcons | Lavisha Rastogi | ON | ON | ON | ON | ON | ON | OFF |  |  |  | DE61143
63 | contract_avengers_2019_q2_s5_de65958 | Honda-After Primary Vehicle Information, the additional assets have the product line drop down and when selecting any asset such as boat, it doesn’t populate the additional fields | 2.61.6 |  | July 8.2019 | Avengers | Maruthi Mettela | ON | ON | ON | ON | OFF | ON | OFF |  |  |  | DE65958
64 | contract_technocrats_2019_q2_s5__de64850 | Honda and ML finance page validaton, for insurance other_provider_name required field validation | 2.62.0 |  | 2019-07-10 | Technocrats | Naveed Khan | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE64850
65 | contract_param_2019_q2_ip__us260351 | NMAC Lease - Aftermarket change | 2.61.6 |  | 2019-07-09 | Param | Kiran Borawake | ON | ON | ON | ON | [6 empty] | US260351
66 | contract_technocrats_2019_q2_ip__de52409 | Disabling cancel contract button after submitted for funding | 2.62.0 |  | 2019-07-11 | Technocrats | Naveed Khan | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE52490
67 | contract_falcons_2019_q2_s6__de65603 | YMMT dropdown year for lease AHFC | 2.61.9 |  | 2019-07-16 | Falcons | Shobhit Bajaj | ON | ON | ON | ON | [6 empty] | DE65603
68 | contract_technocrats_2019_q2_ip__de60046 | Finance page validaton for insurance section provider when other is selected and Other is entered in Provider name | 2.63.0 |  | 2019-07-18 | Technocrats | Naveed Khan | ON | ON | ON | OFF | OFF | OFF | OFF |  |  |  | DE60046
69 | contract_nights_watch_dms_f38228_2019_q2_s5 | implemented adding few validations wrappers around the existing codes to filter ghost fields and normalized data in connection with the mongo documents. | 2.62.0 |  | 2019-07-02 | Nights Watch | Chuck | ON | ON | ON | ON | OFF | ON | OFF |  | OFF |  | F38228 (https://ghe.coxautoinc.com/DT-SFI/dt/pull/350)
70 | contract_nutsandbolts_2019_q2_s5_US255740 | Insurance and Aftermarket products | 2.62.0 |  | 2019-06-21 | Nuts and Bolts | Shawket | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | US255740
71 | contract_nutsandbolts_2019_q2_s5_us258720 | XML Customization | 2.62.0 |  | 2019-06-28 | Nuts and Bolts | Shawket | ON | OFF | OFF | OFF | OFF | OFF | OFF |  | OFF |  | US153102
72 | contract_nutsandbolts_2019_q2_s5_US115221 | Signing Rules for Wisconson. | 2.62.0 |  | 2019-06-26 | Nuts and Bolts | Shawket | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | US114529
73 | contract_nutsandbolts_2019_q2_s5__us218910 | Fees fields, made changes to react currency react componant. | 2.62.0 |  | 2019-07-15 | Nuts and Bolts |  | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | US218910
74 | contract_nutsandbolts_2019_q2_s5_de55678 | Credit App document status on FPP. Only for DTCOM Spot contracts. | 2.62.0 |  | 2019-07-01 | Nuts and Bolts | Liping | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE55678
75 | contract_nutsandbolts_2019_q2_s5_de61053 | Contract Cancel, DMS import | 2.62.0 |  | 2019-06-21 | Nuts and Bolts | Shawket | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE61053
76 | contract_enciphers_2019_q2_ip | For DTCOM Only, Retail finance page calculations in case of 0% APR GFR Lease - more than allowable upfront charges added on finance UI | 2.62.0 |  | 2019-07-09 | Enciphers | Shradha More | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | US260990, US231355
77 | contract_param_2019_q2_s5_de51850 | Nissan - Contract edit page displaying fields when no values are entered | 2.61.0 |  | 2019-06-28 | Param | Sinkita Jain | ON | ON | OFF | OFF | OFF | OFF |  |  |  |  | DE51850
78 | contract_technocrats_2019_q3_s1__de66646 | Cancel contract button on fpp page. that made visible on fpp return page. | 2.62.2 |  | 2019-07-23 | Technocrats | Naveed Khan | ON | ON | ON | ON | OFF | ON | OFF |  | ON |  | DE66646
80 | contract_avengers_2019_q2_s5 | CR 46779 Preselected fees | 2.62.0 |  | 2019-07-22 | Avengers | Maruthi | ON | ON | ON | ON | OFF | ON | OFF |  | OFF | ON | US234805
81 | contract_technocrats_2019_q3_s1__us143705 | Vault transfer error on edit contract. Cancel or edit a signed contract, reprocess and sign again. | 2.63.0 |  | 2019-07-23 | Technocrats | Naveed Khan | ON | ON | ON | OFF | OFF | OFF | OFF |  |  |  | US143705
82 | contract_param_2019_q3_s1__de67084 Please make sure all feature toggle should be enabled from sr.no 45: dcon_lease_modal contract_falcons_q2_s2_de60013 contract_param_2019_q2_s5__de59087 Enable at DTCOM tenant only | Defect: Taxes modal in Unifi is wiping out data other than "Tax on Cap Cost Reduction" and no longer throws interior modal error as indicator to user | 2.62.3 |  | 2019-07-26 | Param | Kiran Borawake | ON | OFF | OFF | OFF | OFF | OFF | OFF |  | OFF |  | DE67084
83 | contract_param_2019_q3_s1__us272811 | USB- Does not allow Non taxable option to be chosen in State on MI | 2.62.3 |  | 2019-07-26 | Param | Kiran Borawake | ON | ON | ON | ON | OFF | OFF | OFF |  | ON |  | US272811
84 | contract_nutsandbolts_2019_q3_s1_us265832 | Added new action on FPP page. | 2.63.0 |  | 2019-07-24 | Nuts and Bolts | Najeeb | ON | ON | ON | OFF |  | OFF |  |  |  |  | US265832
85 | contract_avengers_2019_q2_s5_de65703 | HPP and Credit Disability values | 2.62.2 |  | 2019-07-22 | Avengers | Anushree Roy | ON | ON | ON | ON | OFF | ON | OFF |  | OFF | ON | DE65703
86 | contract_avengers_2019_q2_s5_de65958 | Marine Assets Sorry PAge | 2.62.2 |  | 2019-07-22 | Avengers | Anushree Roy | ON | ON | ON | ON | OFF | OFF | OFF |  | OFF | ON | DE65958
87 | contract_enciphers_2019_q3_s1 | 1. Validations for allowable Capitalized charges on finance UI for GFR lender 2. Display of 'Comprehensive Deductible' and 'Collision Deductible' fields on finance UI for DTCOM | 2.63.0 |  | 2019-07-17 | Enciphers | Shradha More | ON | OFF | OFF | OFF | OFF | [5 empty] | US214279, US231357
88 | contract_param_2019_q3_s1__DE66779 | Summary Screen - Contract section is displaying credit app amt fin instead of contract amt fin for statuses | 2.62.3 |  | 2019-07-30 | Param | Sinkita Jain | ON | ON | ON | ON | OFF | OFF | OFF |  | OFF
89 | contract_param_2019_q2_s5_de51850 | Contract edit details page. Remove fields not entered on contract finance page ie Flex Cash | 2.63.0 |  | 2019-07-22 | Param | Sinkita Jain | ON | ON | ON | OFF | OFF | OFF | OFF |  |  |  | DE66779
90 | contract_avengers_2019_q3_s1__de29488 | Balloon/Retail - Pre-submit rule is not triggered for provider and address field for Credit Disability Insurance product | 2.63.0 |  | 2019-07-30 | Avengers | Anushree Roy | ON | ON | OFF | OFF | OFF | [5 empty] | DE29488
91 | contract_avengers_2019_q3_s1_de67431 | Unexpected 'This field is required.' Error for VIN input on Contract - Vehicle Page | 2.63.0 |  | 2019-07-30 | Avengers | Anushree Roy | ON | ON | OFF | OFF | OFF | [5 empty] | DE67431
92 | lender_eligibility | Use the new LET tool during the digital contracting flow instead of old table | 2.62.0 |  | old | Param | Unknown | OFF | ON | OFF | ON | ON | OFF | OFF |  | ON
92 | contract_avengers_2019_q2_s5 | PRe Selected Fees | 2.63.0 |  | 2019-07-30 | Avengers | Anushree Roy | ON | ON | OFF | OFF | OFF | [5 empty] | DE68177 DE68073
93 | contract_avengers_2019_q3_s2_de62068 | Trade-in VIN decoder screen is displayed on Contract Vehicle Page | 2.63.0 |  | 2019-07-30 | Avengers | Anushree Roy | ON | ON | OFF | OFF | OFF | [5 empty] | de62068
94 | Shrikant | Shrikant
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contract Sub feature name that been set on the Feature toggle page
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: list the high level workflow which are impacted
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Major Release version
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date when the feature toggle PR got merged to master
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team owning the Feature toggle
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Responsible to set and validate the Feature toggle and maintain them in respective environments
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feature toggle GitHub PR link which got merged to master
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feature toggle GitHub Remove PR link which will get merged to master once the code is push to production
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date when the feature toggle remove PR merged
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current Feature status on the respective environment

## LKGS (hidden)
Feature Name | Status | Release | Updated by | Last Status | Note
contract_nutsandbolts_2019_q2_s2 | ON | 2.60.0
contract_falcons_q2_s2_de60013 | OFF
contract_enciphers_2019_q2_s3 | OFF | 2.60.2
contract_avengers_2019_Q2_S3_US220764 | ON | 2.60.1
contract_avengers_US212425_2019_Q2_S2 | ON | 2.60.1
contract_avengers_2019_q2_s3 | OFF | 2.60.3
contract_avengers_2019_Q2_S3 | ON | 2.60.1
contract_param_2019_q2_s4 | ON | 2.60.4
dms_ins_filter | ON | 2.60.1
Contract_PARAM_2019_Q2_2 | OFF | 2.60.0
contract_param_2019_q2_s3 | ON | 2.60.2
contract_falcons_2019_q2_s3__de54719 | ON | 2.60.2
dcon_lease_modal | OFF | 2.60.0
contract_avengers_2019_q2_s3_DE62851 | ON | 2.60.0
coapp_ssn_validation | ON | 2.60.0
dob_under_eighteen | ON | 2.60.0
ContractAvengers_2019_Q2_S3 | ON | 2.60.0
contract_avengers_2019_Q2_S2_DE59481 | ON | 2.60.0
dcon_atomic | OFF |  |  |  | Only for Specific Lender
vin_validation | ON
lender_eligibility | ON
Contract_nightswatch_DE57199_2019_Q2_S1 | ON
contract_nutsandbolts_2019_q2_s3 | ON
contract_avengers_2019_Q2_S2 | ON
Contract_PinkTeam_remove_cache | ON
modifiers_page_spot_flow | ON
contract_param_2019_q2_s4_DE60013 | ON
Contract_Technocrats_US247941_2019_Q2 | ON
contract_technocrats_2019_q2_s4_de60302 | ON
dcon_balloon | ON |  |  |  | States Specific
contract_dms_subscription | ON |  |  |  | Only for Specific Dealer
one_pay | ON |  |  |  | Only for Specific Lender
adapter_subscribed | ON |  |  |  | Only for Specific Lender
atomic_xml | ON |  |  |  | Specific Lender 113431037 for both RETL ¦ LEAS
standard_atomic_xml | ON |  |  |  | Specific Lender 113431037 for both RETL ¦ LEAS
standard_classic_xml | ON |  |  |  | Only for Specific Lender for Lease Product Only
remote_signature | ON |  |  |  | Specific Dealer: 400016600
new_contract_details_page | ON |  |  |  | Specific Lender 121850004
doc_center_logs | OFF |  |  |  | Only for Specific Lender
chase_feature_toggle | OFF |  |  |  | Only for Specific Lender
nmac_pilot_atomic_xml | ON |  |  |  | Only for Lender 113430964 ¦ Dealer DE, KS, IA
fugu_async | OFF
contract_falcons_2019_q2_s4__de60735 | OFF